## Study description
Countries | `FR | ES | IT | BE | GER
N° of patients | 700
Type of study | RCT 2 arms, simple blind (assessor)
Randomization | 2 arms, 1:1
Enrollment period | 12 months
Duration for a participant | 6 months
Ethics submissons | May - June 2025
Study start | November 2025

## Needs
Item | CRO | Edra
Protocol writing |  | X
Sample size review | X
Protocol review | X
Synopsis writing |  | X
Biostat writing of endpoints and statistic section of protocol | X
SAP writing | X
Synopsis translation | X
eCRF spec |  | X
eCRF platform | X
ePRO platform | X
Providing of information for CNIL authorization | X
EDC translation | X
ICF writing |  | X
ICF review other countries | X
ICF translation | X
EC submission FR |  | X
EC submission other countries | X
Feasibility study FR |  | X
Feasibility study other countries | X
SIV preparation, organization and realization in person or remote + collecting SIV documents FR | X
SIV preparation, organization and realization in person or remote + collecting SIV documents other countries | X
Update of eTMF | X
Contract handling FR |  | X
Contract handling other countries | X
ISF preparation and shipping FR | X
ISF preparation and shipping other countries | X
Site payment handling | X
Site follow-up other countries | X
Biostat analysis | X
Monitoring per visit FR | X
Monitoring per visit other countries | X
Data management eCRF | X